Sample Event Planning Timeline

Four Months

Develop program concept

Arrange meeting with program committee members

Choose potential dates, keeping in mind holidays and School breaks

Develop a preliminary budget of projected expenses and revenue

(printing, mailing, refreshments, travel, room rental, and speaker fees, if applicable)

Decide on registration

Submit a request to the library administration

Send confirmation letters once commitments are made

Three Months

Plan a marketing and publicity strategy (mailing information in the

club newsletter, invitation, save the date postcard, or broadcast email)

Create draft flyers/press release with input from committee members. Several people should proofread the final draft before it is printed

Eight to Twelve Weeks

Distribute/Mail/email flyers

Make catering arrangements (if applicable)

Arrange equipment and setup of facilities

Six Weeks

Send press release to local media

Organize your staff/volunteers for the day of the event

Four Weeks

Copy all materials needed for the event

Call speaker/presenter to confirm details

Create signage

Two Weeks

Mail/email directions to speaker/presenter

Contact committee to confirm on–site assignments

One Week

Call in final catering numbers (if applicable)

Gather all materials, signs, etc. for the event

Day of Event

Review room setup/AV setup and supplies

Have program flyers and surveys available

After Event

Collect surveys and program flyers

Tally information and incorporate into quarterly report and planning